## daily
Date | Customer | Product Line | Project (CAVM P/N) | ISSUE Description | WIP/Done is the past week/Status Updates | Duraton (Hours)
20180910 | H3C | Server | Harbin | link up issue during power cycling | Use the commands to collect more debug info on H3C's board | 0.5
20180910 | H3C | MSR | CN96XX | CN96XX introduction | Eric's meeting with H3C management: check their testing case of forwording | 2
20180910 | H3C | Security | CN96XX | CN96XX introduction | Eric's meeting with H3C management: check their testing case of forwording/SSL | 2
20190911 | H3C | Server | Harbin | Update CQs | OEM meeting, and update all the latest status of CQs | 4
20190911 | Sugon | Server | BCM57840 | How many Mac addresses for each card. | Check on the card, and email to sPM | 2
20190911 | Sugon | Server | BCM57840 | 4x10G windows driver | Cont00102779 sugon windows driver doesn't work with 4x10G firmware verified successfully with WindowsDriverInstaller_34xx_84xx_20.20.5.19.zip | 3
20190911 | H3C | Security | CN83XX | pcie2sata issue | On H3C's board, no issue with kernel4.9. | 0.5
20190912 | H3C | Server | Harbin | iscsi issue | waiting for H3C's switch board. No schedule of new chasis | 0
20190912 | H3C | Security | CN96XX | CN96XX | prepare for H3C's testing cases | 0
20190912 | Huawei | NGFW | CN7809 | HFA issue | Engineer team didn't have resource before end of October | 0.1
20190913 | H3C | Server | Harbin | link up issue during power cycling | H3C can't reproduce this issue on the two setups since this Monday. They are working on reproducing and checking what had been changes on the setups. Working on how to use sharepoint | 3
20180914 | H3C | Storage | Handan | project status update | the hardware is ready, Software is in testing. There are two open issues in this project, Cont00101708 and Cont00101592. H3C expected closing these two issues by the end of Q3. They are planning to start their TR4 procedure in Q4. The GA is targeted at Q1 2019. | 3
20180914 | H3C | Server | Harbin | package release of signed uefi and the fix of Cont00097594 | Cont00097594 (configuration saving issue) | 1
20180914 | H3C | Security | CN96XX | SSL testing cases for CN96XX opportunities | Discussing H3C's testing cases. Rise the priority of the crypto-core issue of cn7809 | 5

## next
Customer | Product/Project (CAVM P/N) | Issue Description | Actions
Sugon | BCM57840 | Questions about Mac address for BCM57840 adapter | //2x20G config: mac addr counts npar 4x2 = 8个； lldp 2； iscsi: 每个物理端口上，只有一个Npar接口上可以使用iscsi, total is 4. fcoe: 每个物理端口上，只有一个Npar接口上可以使用fcoe. total is 2. WWNN/WWPN各有几个：需要烧写吗？ ISCSI: two iSCSI offload protocol can be enabled per port on any two partitions for a total maximum of 8 on bcm57840 devices FCOE: one FCOE offload protocol can be enable per port on any one of partitions for a total maximum of four on bcm57840 devices //4x10G config: mac addr counts Npar ： 4 port x 2 = 8 MACs； lldp 4；iscsi：8；fcoe：4 --- ? WWNN/WWPN各有几个：需要烧写吗? （1）2X20G的网卡的Mac数量是16个，实际上每个端口虚拟出四个，另外8个是如何分配的？ （2）4X10G网卡打开NPAR，需要几个MAC，怎么分配？不打开NPAR，需要几个？ （3）WWPN和WWNN和MAC的关系？ （4）WWPN和WWNN是自动生成的？还是需要我们刷写？ （5）实测2x20G网卡有两个WWPN和2个WWNN。理论上不应该是一张网卡对应一个WWNN，对应两个WWPN。 --- It doesn’t matter how many ports that you need 16 Mac addresses. You would have 4 NPAR for each port on two port adapters, you have two NPAR for each port on 4 port adapters. Each NPAR needs two MAC addresses, one for NIC, one for iSCSI. If you don’t need FCoE / iSCSI, it’s same that you need 16 MAC addresses.
H3C | Security (CN83xx) | pcie2sata issue | waiting for TME's feedback. On H3C's board, no issue with kernel4.9
H3C | Security(CN96XX) | testing cases of forwarding/SSL
H3C | Security(7809) | crypto-core issue
H3C | Security(cn83xx) | async mode of CPT
H3C | MSR(CN96XX) | testing cases of forwarding
huawei | NGFW | hfa issue | Engineer team didn't have resource before end of October
Baidu | SecureNic(Liquidio) | OVS-QoS requirement | waiting for design details from engineer.
H3C | harbin | link up issue during power cycling | (Cont00103032 ) H3C can't reproduce this issue on the two setups since this Monday. They are working on reproducing and checking what had been changes on the setups.
H3C | harbin | Cont00101333 iscsi issue | waiting for H3C to ship switch board to HQ
H3C | harbin | update project status in sharepoint | get the start date and end date of H3C's QA stage. UEFI configuration saving issue(Cont00097594 ) and Signed UEFI issue for GA.
H3C | harbin | QinQ issue | Cont00103102 need fix before Sep 15th.
H3C | Handan | project status
HOME | House | No. 48 Ningbodao | 夫妻双方征信报告，建设银行 一类储蓄卡和对账簿 10月底 打协议+面签。 需准备首付 171x60%=102.6万 一个月后（贷款到位后）过户。需准备税费：171x3%=5.13万 一个月后，拿房本。一周后物业交割。
HOME | House | Jingzhili | 2018-9-6清贷。10个工作日后，可电话到银行，查询进度。电话24150306
Sugon | BCM57840 | 4x10 windows driver | verify Cont00102779 sugon windows driver doesn't work with 4x10G firmware 2018/07/30 Vikas: These hw ids are added in evbd v7.13.151a and bxnd60 v7.13.137.0.
H3C | Harbin | package release of signed uefi and the fix of Cont00097594 | provide Linux_FWupg_34xx_84xx_2.10.59.zip to H3C. Waiting for H3C's feedback
H3C | Handan | Cont00101523 Cont00101708 Cont00101592

## weekly
[WSR]Shanping.Yi, Greater China